## Slide 1
Lecture 3 : Project management
CSI342 Systems and Design

## Slide 2: Learning Objectives
At the end of this lecture, students should be able to:
Define project management
Identify the responsibilities of the project manager
Identify the details of a project plan, management tools
Apply project management tools

## Slide 3: Introduction
Project: A planned undertaking of related activities to reach an objective that has a beginning or an end.
Stakeholder: A person who has an interest in a new or existing Project
Project Sponsor: A member of an organization or department that initiates a project request and is responsible for high level support of the project.
Project Manager: A person with diverse set of skills-general management, leadership, technical, conflict management and is responsible for initiating, planning, executing, controlling & monitoring and closing down a project.
3

## Slide 4: Overview of Project Management
Project management
  Planning, scheduling, monitoring & controlling, and reporting on information system development
  Project Management is the process of planning and controlling the development of a system within a specified time frame at a minimum cost with the right functionality
What shapes a project?
  Successful projects must be completed on time, within budget, meet requirements, and satisfy users

## Slide 5: Overview of Project Management
What is a project triangle?
  Challenge: find optimal balance among the factors
    Any change in one leg will affect the other legs

## Slide 6: Skills of Project Manager?
The project manager is a systems analyst with a diverse set of skills- management, leadership, technical, conflict management, and customer relationship- who is responsible for initiating, planning, executing, and closing down a project.

## Slide 7
A project manager has the primary responsibility for managing the project
Most managers take responsibility at some stage of the project for the following activities:
Proposal writing
Project planning and scheduling
Project cost
Project monitoring and review
Personnel selection and evaluation
Report writing and presentation
Responsibilities of a Project manager

## Slide 8: Project managers responsibilities
Proposal Writing- this is the first stage in a software project. The proposal describes the objectives of the project and how it will be carried out. It usually includes costs and schedule estimates and justifies why the contract should be awarded to a particular organization or team
Project planning and scheduling – this is concerned with identifying the activities, milestones and deliverables produced by a project. A plan is drawn up to guide the development towards the project goals. Necessary costs and resources estimates are also included.

## Slide 9: Project manager’s responsibilities
Milestones are recognizable end points of a software process activity. At each milestone, there should be a formal output, such as a report that can be presented to management. Milestones should represent the end of a distinct, logical stage in the project.
A deliverable is a project result that is delivered to the customer. It is delivered usually at the end of some major project phase such as specification or design.

## Slide 10: Project managers responsibilities
Project monitoring and reviews – Monitoring is a continuing project activity. The manager keeps track of the progress of the project and compare actual and planned progress and costs. Formal project management reviews are usually established to ensure the overall progress and technical development align with the goals of the organization paying for the software.
Personnel selection – managers have to select qualified and skilled people to work on projects
Report writing – managers are usually responsible for reporting on the project to both the client and contractor organization.

## Slide 11: Details of Project Plan
A project plan sets out the resources available to the project, the work breakdown, and a schedule for carrying out the work
Most project plan documents would include:
Introduction: brief description of objectives of the project and sets out the constraints (eg budget, time) that affect the project management
Project organization : the way in which the development team is organized, the people involved and their roles in the team
Risk analysis : describes possible project risks, the likelihood of these risks and the risk reduction strategies proposed

## Slide 12: Details of a project plan
4) Hardware and software resource requirements : specifies the hardware and support software required to carry out the development. If hardware has to be bought, cost estimates and delivery schedule are included
5) Work breakdown : sets out the break down into activities and identifies the milestones and deliverables associated with each activity
6) Project schedule : shows the dependencies between activities, the estimated time to reach each milestone and the allocation of people to activities
7) Monitoring and reporting mechanism : defines management report to be produced, when expected and the project monitoring mechanism used

## Slide 13: Project Planning & Scheduling
Identifying and Selecting System Development Projects: This process can be performed by
member of top management – Projects identified by top management often have a strategic organizational focus
Steering committee - projects identified by a steering committee reflect the diversity of the committee members, hence such projects have cross functional focus
User department – Projects identified by a user department often have a narrow tactical focus
Development group or senior IS manager - often this is the case with which existing hardware and systems will integrate

## Slide 14: Skills Required in a Project Manager
Leadership – influencing other team members towards attaining a common goal
People mgt – managing team for effective team performance
Effective communication – with management, users & team
Negotiation – with customers, project team, management
Conflict management – smoothing out personality differences
Planning –defining and sequencing activities
Estimating –time and cost of activities and whole project
Problem solving -designing solutions to problems
Time management –monitoring progress
Creative thinking –coming up with new ideas or concepts

## Slide 15: Project Management Process
Project Management Has 4 phases:
Project initiation - Realization of a business need
Project planning - Detailed plans of how to carry out project work
Project execution and control - Doing the work to deliver the product; ensuring the project stays on track
and taking corrective measure to ensure it stays so
Project closure - Formal acceptance of the deliverables
Releasing all resources that were used in the project

## Slide 16: Project Initiation
i. What is the problem?
- Identify the problem that needs to be solved
ii. What are the available resources
- Include staff time, appropriate tools, and capital
iii. What are the project’s risks?
-Often recorded as part of the feasibility study
iv. Establish PM environment and project workbook

## Slide 18: Project Planning
Has an effect on the project outcome
Involves defining clear discreet activities and the work needed to complete each activity
Requires assumptions about availability of resources
Helps avoid unpleasant surprises during the project
Resource planning –getting the right resources and tools at the right time
Basis of controlling the project
Helps compare what has been achieved against what was originally planned
Helps identify problems and risks

## Slide 19: Some deliverables of Planning
Statement of Work (SOW)
“Contract” regarding deliverables & time estimates
The Baseline Project Plan (BPP)
Preliminary Budget: Cost-benefit analysis
Work Breakdown Structure (WBS)
Division of project into manageable and logically ordered tasks and subtasks
Scheduling Diagrams
Gantt chart
Network diagram

## Slide 20: Project Execution
Putting the approved detailed plan into motion
Brings together resources, tasks and schedules
Involves
Executing project plan
Performing project’s activities
Monitoring progress against plan
Are we behind schedule? How could we catch up if so?
Managing changes in the plan
Coordinating people and resources
Communicating project status to various stakeholders

## Slide 21: Project Monitoring & Control
Usually considered part of the execution phase
To ensure project provides an end product that meets the original objectives
Several areas to be monitored:
schedule, costs, resources & quality
Purpose is to run the project as far as possible according to the plan and schedule
In case of deviations from the plan, control actions include
Adjustments to resource allocation
Detailed re-scheduling or re-planning
Cancellation of the project

## Slide 22: Project Close down
Bring the project to a successful end
Actions performed:
Close down the project
Release project resources
Conduct post-project reviews
  Meet stakeholders to get consensus about status & value of project results
Write and publish final report
Close the customer contract

## Slide 23: Project Management tools (Scheduling Tools)
Project scheduling involves separating the total work involved into separate activities and judging the time required to complete these activities
Managers estimate time and resources required to complete activities and organize them into a coherent sequence
When estimating schedules, do not assume that every stage will be problem free, however estimate as if nothing will go wrong, and cover anticipated problems

## Slide 24: The Scheduling Process
Identify Activities
Identify Activity dependencies (Dependencies are those activities that must be completed before the following activity can begin)
Estimate resources for activities (e.g timing/duration)
Allocate people to activities
Create project charts (Activity charts and bar charts)
Go back to estimate resources for activities if need be.

## Slide 25: The Work Breakdown Structure (WBS)
Decomposition of a project into manageable tasks which are logically ordered to ensure a smooth evolution between them
Often portrayed as one of the following
  Graphically as a hierarchical tree
  In a simple outline style
  Tabular list of elements categories and tasks
Project size & complexity determines no. of tasks & level of refinement
  Larger system more detailed
Helps to understand large complex projects

## Slide 26
1. Requirements Collection
0. Customer Ordering Project
2. Design
3. User Documentation
4. Implementation
2.1 Screen Design
2.2 Report Design
2.3 DB Design
4.1 Programming
4.2 Testing
4.3 Installation
Example
WBS for a
Project

## Slide 27: Estimating Task Durations
Project manager must estimate the duration of each task on the WBS
Must consider:
  Size of project team
  Experience of team members
  Time, e.t.c.
Idea is to assign a single value estimation to each task
  Can be difficult if task time estimates are uncertain
  One approach is to use estimates on the next slide

## Slide 28: Types of Duration estimates
Optimistic Duration (O)
Minimum time it would take to perform the task assuming everything goes perfectly as planned
Pessimistic Duration (P)
Maximum amount of time it will take, assuming that nearly everything will go wrong
Realistic Duration (r)
Realistic amount of time required to complete the task, assuming most likely delays
The expected time (ET) is then calculated as
ET = O + (4*r) + p
6

## Slide 29: Example: (Time estimates in Weeks)
Activity | O | r | P | ET
1. Requirements Gathering | 1 | 5 | 9 | 5
2. Screen Design | 5 | 6 | 7 | 6
3. Report Design | 3 | 6 | 9 | 6
4. Database Design | 1 | 2 | 3 | 2
5. User Documentation | 4 | 6 | 7 | 5.5
6. Programming | 3 | 5 | 6 | 5
7. Testing | 1 | 3 | 5 | 3
8. Installation | 1 | 1 | 1 | 1

## Slide 30: Develop a preliminary schedule
Define when each activity will be carried out and the resources available to it
  Sequence of activities (& precedence relationships)
Follows time estimates for each activity
  Schedule may need to be refined to include changes or extra activities to help risk management
Common tools used
  PERT chart or Network Diagram
  Gantt chart

## Slide 31: PERT (Program Evaluation Review Technique or Network Diagram)
Used to schedule, organize and coordinate project tasks
Tasks on parallel paths can be done concurrently
Developed to simplify planning and scheduling of large and complex projects
Useful when the individual task’s time estimates are uncertain
Shows precedence
  Activities to be completed before the next one begins.
Major components:
  Nodes : activities
  Arrows: sequencing of activities

## Slide 32: ET with Preceding Activities (Dependencies)
Activity | ET | Preceding Activity
1. Requirements Gathering | 5 | -
2. Screen Design | 6 | 1
3. Report Design | 6 | 1
4. Data Base Design | 2 | 2,3
5. User Documentation | 5.5 | 4
6. Programming | 5 | 4
7. Testing | 3 | 6
8. Installation | 1 | 5,7

## Slide 33: The Critical Path
PERT chart helps identify project’s critical path
  Longest path through the activities
From project inception to its completion
  Determines total time required for the project
  Gives shortest time to complete the project
  Any delays on the critical path will delay the whole project
  Should be monitored regularly
  All activities on this path have zero float

## Slide 34: PERT Chart
2
4
1
5
3
6
7
8
ET=5
ET=1
ET=5.5
ET=2
ET=6
ET=3
ET=5
ET=6

## Slide 35: Calculating Critical Path
From the above PERT chart, Calculate the Critical Path as follows:
There are 2 Paths here, namely
  1, 2, 4, 6, 7,8 (Black Line)
  1, 3, 4, 6,7, 8 (Red Line)
Either path gives
5+6+2+5+3+1 = 22 Weeks

## Slide 36: Alternative Example
Task /Activity | Duration (days) | Dependencies
T1 | 8 | 
T2 | 15 | 
T3 | 15 | T1(M1)
T4 | 10 | 
T5 | 10 | T2,T4(M2)
T6 | 5 | T1,T2(M3)
T7 | 20 | T1(M1)
T8 | 25 | T4(M5)
T9 | 15 | T3,T6(M4)
T10 | 15 | T5,T7(M7)
T11 | 7 | T9(M6)
T12 | 10 | T11(M8)

## Slide 37: Using Gantt Charts for Project scheduling
Points to note
  Bars represent each task or activity
  The length of each bar represents the relative length of the task
  Time may be indicated on the horizontal dimension
  Description of activities make up the vertical dimension
  Completed projects or parts may be shaded in colour different from the uncompleted
  Bars representing activities are drawn to scale (i.e. the size of the bar indicate the time it will take to finish task

## Slide 38: Example of Gantt chart

## Slide 39: Risk Management (1 of 2)
A risk is an event that could affect the project negatively
Steps in risk management
  Develop a risk management plan
  Identify the risks
  Analyze the risks
    Qualitative and quantitative risk analysis
Qualitative risk analysis evaluates each risk by estimating the probability that it will occur and the degree of impact.
The purpose of quantitative risk analysis is to understand the actual impact in terms of dollars, time, project scope, or quality

## Slide 40: Risk Management (2 of 2)
  Create a risk response plan
    Proactive effort to anticipate a risk and describe an action plan to deal with it
  Monitor risks

## Slide 41: Summary
Project Management involves 4 phases
  Project Initiation
    Define the Problem - Problem definition is produced after completing interviews, observations, document analysis with users (See case study Catherine catering example. Pg 87-88, Systems Analysis and Design by Kenneth Kendall)
    Selection of projects – Projects come from different sources for many reasons. Not all should be selected for further study. Be clear about reasons for recommending a systems study on a project
  Apart from the general considerations, there are 5 specific considerations for project selection as shown below:

## Slide 42: Summary
Specific criteria for Project Selection
  Backing from management
  Appropriate timing of project commitment
  Possibility of improving attainment of organizational goal
  Worthwhile project compared with other ways the organization could invest its resources
Project planning- Plan how to execute the project as already discussed in Project management
Project execution - The concentration of the rest of the course.
Project Closure – close project formally